## Standup Meetings
Date | Sprint | What did I do yesterday? | What will I do today? | Are there any blockers?
Day 1 (Sprint 1) | Sprint 1 | Initialized Vite frontend and Express backend architecture. | Implemented JWT auth and SQLite user profile schemas. | None
Day 3 (Sprint 1) | Sprint 1 | Integrated Gemini API for resume parsing and SWOT analysis. | Built deterministic fallback engine for offline reliability. | Handled rate limit handling with fallback heuristics.
Day 6 (Sprint 2) | Sprint 2 | Curated 180 standardized tech internship postings. | Implemented 4-way semantic chunking and 256-dim vector store. | None
Day 9 (Sprint 2) | Sprint 2 | Developed multi-factor matching formula (Skills, Role, Location). | Ran benchmark test suite across 6 multi-domain student profiles. | None
Day 12 (Sprint 3) | Sprint 3 | Built 5-category Skill Gap Agent and learning roadmaps. | Developed Resume & Cover Letter Customizer with anti-hallucination check. | None
Day 15 (Sprint 3) | Sprint 3 | Built Mock Interview Coach with 3D scoring and Web Speech API. | Implemented Conversational Career Assistant orchestrator and 3D UI. | None
Day 18 (Sprint 4) | Sprint 4 | Designed 10-stage application lifecycle schema and API endpoints. | Built Kanban drag-and-drop UI with urgency deadline indicators. | None
Day 21 (Sprint 4) | Sprint 4 | Added Application Analytics summary metrics and table filter controls. | Executed Milestone 4 test suite (21 assertions) and end-to-end pipeline validation (105 assertions total). | None