## Defect Tracker
Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
WASM file path ENOENT error on serverless SQLite | Sprint 1 | Harsh | Environment / Configuration | Switched to pure JS sql-asm engine with fallback to sql.js locateFile. | 2026-09-08 | Closed | Database now initializes locally and serverless without path errors.
Gemini API quota exceeded causes unhandled promise rejection | Sprint 1 | Harsh | Exception Handling / AI Service | Implemented intelligent deterministic heuristic fallback engine. | 2026-09-10 | Closed | System maintains 100% uptime even when offline or quota-limited.
Resume skill parser duplicated case-insensitive skill names | Sprint 1 | Harsh | Data Processing / Logic | Added Set deduplication and title-case normalization in parser. | 2026-09-11 | Closed | Clean, non-redundant skill taxonomy returned.
RAG vector cosine similarity returning NaN on zero vectors | Sprint 2 | Harsh | Algorithm / Mathematics | Added epsilon guardrail (1e-9) in vector magnitude calculation. | 2026-09-13 | Closed | All similarity scores compute cleanly between 0.0 and 1.0.
Cover letter textarea text unreadable due to low contrast | Sprint 3 | Harsh | UI / UX Visual Defect | Updated textarea background to #0f172a and text color to explicit #f8fafc. | 2026-09-17 | Closed | Verified text is bright, crisp, and high-contrast.
Navigation bar overlapping with content when sidebar toggled | Sprint 3 | Harsh | Layout & Responsiveness | Tied main dynamic marginLeft directly to isSidebarCollapsed state. | 2026-09-17 | Closed | Layout transitions smoothly (4.5rem to 16rem) with zero overlap.
Redundant "Go to Dashboard" button appearing on landing page | Sprint 3 | Harsh | UI Navigation Flow | Restricted header actions so Landing page strictly displays Sign In and Log In. | 2026-09-17 | Closed | Landing page header is uncluttered and displays only login options.
Kanban drag-and-drop card position reset on rapid state toggling | Sprint 4 | Harsh | UI / Drag and Drop State | Optimized optimistic UI updates with immediate local state mutation before backend synchronization. | 2026-09-22 | Closed | Kanban board transitions smoothly without flicker or position jump.
Application deadline calculation offset by UTC timezone shift | Sprint 4 | Harsh | Date Calculation / Logic | Standardized date parsing using ISO YYYY-MM-DD string comparisons. | 2026-09-24 | Closed | Urgency badges accurately calculate days remaining in user's local timezone.